## Task List
DM CaT - Architecture Tiger Team - Task List
Last updated: | 2020-03-06
Source | In-Date | Topic | Action Item | Status | Additional Remarks | Responsible | Due Date
Chairman | 2020-03-05 | CWIX2020: Marketing Material | Architectural Products to publish for CWIX visitors. Deliver them to Mark. = marketing-products; background-material. | pending |  | Scott
Waber | 2020-03-05 | Statement of Work | Update and extend the Statement of Work. Clarify the role of the Arch-TT. Align with the expectation from the DM CaT. | pending |  | Waber
DM CaT | 2020-03-05 | Repository Structure | Seperate out the specific implementation things from the generic NCDF Concepts/Functions | pending |  | Waber
Chairman | 2020-03-05 | Operational Context | Operational Context Document: collect possible operational use cases where the concept/framework of NCDF can be applied. | pending |  | Scott
Waber | 2020-03-05 | NCDF Glossary | Implement and maintain the NCDF Glossary | pending | is there already a NCDF Glossary? | Waber
Waber | 2020-03-05 | NCDF FAQ | Idea (tbd): Implement and maintain the NCDF FAQ. Provide consolidated answers to often asked questions? | pending | Example: is there only one SRM? | Waber
Waber | 2020-03-06 | Maturity Levels | Create a new View "NCDF Maturity Level" | pending |  | Waber
Waber | 2020-03-06 | Allied Standards | Based on Briefing from Fahri: Create a new STANAG View ( • Covering Document • Allied Standards (common/obligatory/agreed) - SRD | pending |  | Waber
Waber | 2020-03-06 | Different Concepts | Based on the INT-CORE eISA Briefing from Rytis: Create a view with competing or complementary concepts. Describe what capabilities & functions are "delegated". | pending |  | Waber
GIT Issue #01 | unkown | Adapt L4.1 Vew | Update to include the Message Builder Software Component. The Message Builder Software Component takes selected MIM elements and the NCDF XML Naming and Design Rules and generates the XSD which describes the message to be used to import an information product into the NCDF data lake. The XSD is part of the IEPD. This understanding needs clarification, the existing L4.1 on boarding view updating and a new P3 view developed to show how this tool is made up. | pending |  | Waber
GIT Issue #02 | unkown | NCDF Governance view | Create NCDF Governance view to enhance existing C2 view. As mentioned in the NCDF Governance discussion, the governance view incorporates many of the elements already in place in the existing NCDF Architecture C2 views with stakeholders having desired goals and outcomes. Update the existing C2 view or generate a new C2 view to show the governance process | pending |  | Scott
GIT Issue #03 | unkown | Archi Errors | Review Archi Validation Errors and Correct The Archi Validation tool shows a number of warnings for the NCDF model which need clearing up. | pending |  | Waber
GIT Issue #04 | unkown |  | Document the Architecture Views and Elements The Architecture Views and Elements need to be documented. Example documentation has been added to the L7 Digital Identity view. | pending |  | Waber
GIT Issue #05 | unkown | Motivation view | Add Motivation view Add in NCDF Motivation view including goals, outcomes, requirements and constraints. This should be deconflicted with existing motivation views. | pending |  | deFerrante
GIT Issue #06 | unkown |  | Publish NCDF-Architecture for non-architects Question 1: Format html-export create jasper-standard-pdf Question 2: Plattform Tidepedia - NCDF Page: https://tide.act.nato.int/tidepedia/index.php/NATO_Core_DataFramework(NCDF)_Portal Github | pending |  | waber
GIT Issue #07 | unkown |  | Phrase architecture principles for the main NCDF-function areas Our common understanding of NCDF and data lake approach should be phrased as a collection of architecture principles. These principles should be influenced also by industry data lake approaches (eg. O-BDL from The Open Group) Example: Data Ingestion: Principle: every data that is ingested to the NCDF Data-Lake is translated in conformance to the SRM | pending |  | Waber
GIT Issue #08 | unkown |  | Include the "Data Sharing Capability" From the FMN discussion, the goal of the DM CaT is to improve cross COI data sharing. This was described as a "data sharing capability". This should be incorporated into the motivational views. It was clarified that the Data Pool/Lake is one way of achieving data sharing, there will be other structures that facilitate data sharing (e.g. SOA) I have updated the architecture to include a more refined access control mechanism. This includes the access control node amendment in L2 view to show that it controls access to the data lake. The concept of digital identity and the link to attributes for access was added as an L7 view linking to the SAML concept. The other L4 views were also updated to include the Access control alterations. A P6 view was also created to define how the XACML control would operate. | pending
GIT Issue #09 | unkown |  | FMN: create a NCDF-contribution-view to the different spirals Transfer long word documents to a simple program view. | pending |  | waber
GIT Issue #10 | unkown |  | Create an L7 view for the SRM and related information elements Building from the initial powerpoint view of SRM and related descriptive metadata elements create an L7 view which links the concepts. | pending |  | deFerrante
GIT Issue #11 | unkown |  | Create CWIX 2020 P1/3 views Building on from the CWIX 2019 P1/3 views augment with CWIX 2020 views. Needed for CWIX MPC. | pending |  | scott
GIT Issue #12 | unkown |  |  | pending
GIT Issue #13 | unkown |  | Provide Overview on the NAF Version 4 Views as a reference 20191107 Requested by Vincenzo de Sortis | pending |  | scott
GIT Issue #14 | unkown |  | Time aware roadmap with Archi The aim is to keep all architectural work in one repository. we will have different capability configurations for the future CWIXs in the NCDF environment. Problem: how to modell different connections that changes over time. Sparx EA term: time aware modelling. Next steps: Ian: task BizzDesign (Langhorst) to reflect and propose way ahead Ian/Severin: run tests in git | pending |  | none
GIT Issue #15 | unkown |  | Documentation: way of architectural working in NCDF how to label new views (Creator; Source; Description) naming conventions (time based, etc.) who is allowed to do what (now: everyone can changes everything) | pending |  | none
GIT Issue #16 | unkown |  | Check-out: use Git Project Board for organizing Group Work | pending |  | waber
GIT Issue #17
GIT Issue #18
GIT Issue #19
GIT Issue #20

## Members Arch TT
DM CaT - Architecture Tiger Team - Task List
Last Name | First Name | Nation | Email Official | Phone Official | Email Private | Phone Private | Possible Chats | Collaboration International
Scott | Ian | UK | Ian.Scott526@official.mod.uk | +44 79 631 25 342
Waber | Severin | CHE | severin.waber@vtg.admin.ch | +41 79 669 50 87 | severin.waber@hispeed.ch | +41 79 669 50 87 | WhatsApp, Threema Works, Signal | Webex
de Ferrante | Bernardo | NED | B.d.Ferrante@mindef.nl |  | bdeferrante@trinedmail.nl
Pablo | Cayetano | ESP | pcayetano@ext.mde.es